## Project Scoring Sheet
Basin | Project Names | FCGMA Evaluation Criteria Scores | [25 empty] | TOTAL POINTS
|  | Water Supply |  |  |  | Timing / Feasibility | [13 empty] | Cost & Funding | [5 empty] | Additional Benefits
|  | Total Sustainable Yield/ Supplemental Water/ Reduced Demand | Points | Sustainable Yield/ Supplemental Water/ Reduced Demand Documentation | Points | Project Implementation Timeframe | Points | Development Phase | Points | Status of Approvals, Permits, and Environmental Review | Points | Project Complexity | Points | Land Acquisition | Points | Dependency on Other Projects | Points | Project Lifespan | Points | Water Cost | Points | Funding Match for Construction | Points | O&M Funding | Points | DAC Benefits | Points |  | Notes
OXNARD BASIN | Oxnard AWPF Improvements Phase II | > 7500 AFY | 25 | Conceptual Estimate - limited documentation | 10 | Operational by 2033 | 15 | Conceptual - no feasibility or design, project not well defined | 1 | Expected to take >5 years | 2 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Project is dependent on other unbuilt and unfunded projects | 1 | >20 years | 5 | >$3000 / AF | 1 | No match | 1 | No funding identified | 1 | Yes | 5 | 73 | missing info requested from Oxnard 10/24; Used January 2022 cost estimates, which did not include seawater intrusion barrier per email instructions from City of Oxnard, 10/26/23. $35M in project cost. No O&M cost estimated. SGM grant evaluation list calculates capital cost per AF. year as $5,000. This number was used to determine water cost >$3000/ AF.
| UWCD Ferro-Rose Artificial Recharge of Groundwater | 2500 to <5000 AFY | 15 | Initial FS supporting estimate | 15 | Operational by 2028 | 20 | Initial Feasibility study completed | 3 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | <$500 / AF | 20 | 25 to 50% match | 12 | No funding identified | 1 | Yes | 5 | 111 | Received $2,510,300 in SGM grant funding; $7M in capital cost. $250,000 O&M. $212/AF.
| UWCD Laguna Road RW Interconnection | 500 to <2500 AFY | 10 | Prelim Design and / or modeling supporting estimate | 20 | Operational by 2028 | 20 | 30% engineering design | 4 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Process started but less than 25% complete | 2 | Project is dependent on funded projects under construction | 3 | >20 years | 5 | $500 to $1000 / AF | 15 | >50% match | 15 | No funding identified | 1 | Yes | 5 | 109 | Received $2,651,500 in SGM grant funding; 1500 AF provided; $4.2M capital; $750,000 O&M. $612/AF.
| UWCD Extraction Barrier & Brackish Water Treatment Project | > 7500 AFY | 25 | Prelim Design and / or modeling supporting estimate | 20 | Operational by 2040 | 10 | Initial Feasibility study completed | 3 | Expected to take >5 years | 2 | Very complex relies on unproven technology | 1 | >25 % < 50% complete | 3 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | >$3000 / AF | 1 | No match | 1 | No funding identified | 1 | Yes | 5 | 82 | Missing info requested from UWCD 10/24; Monitoring well component of this project received $2,100,000 of SGM grant funding; UWCD says operational by 2033- Dudek adjusted to 2040 based on permitting timing ; used phase 2 permitting timing for point total. 10,000 AF estimated. $361M in capital. $13M in O&M. $2744/AF (UWCD estimated >$3000/AF)
| UWCD Supplemental Water Purchase | 2500 to <5000 AFY | 15 | Detailed design and / or modeling supporting estimate | 25 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | $1000 to $2000 /AF | 10 | No match | 1 | No funding identified | 1 | Yes | 5 | 106 | Water expected differs from UWCD estimate. They estimate 6,000 AFY with residual benefit. Dudek estimates 3,000 AFY delivered. O&M is anticipated to be $4M, for 3MAF of H2O. That calculates to $1,333/AF.
| UWCD Freeman Diversion Expansion Project | > 7500 AFY | 25 | Conceptual Estimate - limited documentation | 10 | Operational by 2040 | 10 | Initial Feasibility study completed | 3 | Expected to take >5 years | 2 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Project is dependent on other unbuilt and unfunded projects | 1 | >20 years | 5 | <$500 / AF | 20 | No match | 1 | No funding identified | 1 | Yes | 5 | 89 | Assume 25 year capital cost lifetime. $1,440,000 capital cost over 25 years. Plus $1,000,000 O&M. $2.44M per year for 10,000 AF. Total cost $244/AF.
| FCGMA Destruction of Wells to Reduce Interaction between the Upper and Lower Aquifer Systems | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| FCGMA Seawater Injection Barrier Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| FCGMA Transducer Installation | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
PLEASANT VALLEY BASIN | FCGMA Transducer Installation | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
LAS POSAS VALLEY BASIN | Placco LLC Roosevelt Dams | <500 AFY | 5 | Conceptual Estimate - limited documentation | 10 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Permitting and CEQA/ environmental review complete | 5 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | <$500 / AF | 20 | >50% match | 15 | 100% of funding committed | 15 | No | 1 | 116 | The project has already been constructed. Request is for O&M.
| Scholle Ranch Detention Basins | <500 AFY | 5 | No Documentation | 5 | Possible by 2040, but uncertain | 5 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | <$500 / AF | 20 | No match | 1 | No funding identified | 1 | No | 1 | 56 | This project is conceptual for the development of "standard plans and specifications." The intention is to assist individual land owners with understanding how to install different types of detention basins.
| East La Loma Basin | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | FS in progress, project well defined | 2 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | <$500 / AF | 20 | >50% match | 15 | 100% of funding committed | 15 | No | 1 | 104
| FCGMA Monitoring Well Installation | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49
| FCGMA Transducer Installation | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49
| FCGMA NELPMA Water Supply FS | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49

## Previously Submitted
Basin | Project Names | FCGMA Evaluation Criteria Scores | [25 empty] | TOTAL POINTS
|  | Water Supply |  |  |  | Timing / Feasibility | [13 empty] | Cost & Funding | [5 empty] | Additional Benefits
|  | Total Sustainable Yield/ Supplemental Water/ Reduced Demand | Points | Sustainable Yield/ Supplemental Water/ Reduced Demand Documentation | Points | Project Implementation Timeframe | Points | Development Phase | Points | Status of Approvals, Permits, and Environmental Review | Points | Project Complexity | Points | Land Acquisition | Points | Dependency on Other Projects | Points | Project Lifespan | Points | Water Cost | Points | Funding Match for Construction | Points | O&M Funding | Points | DAC Benefits | Points |  | Notes
Oxnard Subbasin | UWCD Nauman-Hueneme Road Recycled Water Pipeline Interconnection | 500 to <2500 AFY |  | Prelim Design and / or modeling supporting estimate |  | TBD |  | Initial Feasibility study completed |  | Underway and approvals expected < 3 years |  | Low complexity, uses readily available proven technology |  | Not required or all acquisitions an/or easements complete |  | Dependency on Other Projects |  | >20 years |  | $500 to $1000 / AF |  | No match | 1 | No funding identified | 1 | Yes |  | On Hold | This project is on hold pending completion of the Laguna Road RW Interconnection
| FCGMA Installation of multi-depth monitoring wells at two locations in the Oxnard Subbasin | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | NA |  | NA |  | NA |  | No | 1 | Funded | Received $737,800 in SGM grant funding
| FCGMA Installation of 3 shallow monitoring wells in the Oxnard Subbasin | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | NA |  | NA |  | NA |  | No | 1 | Funded | Received $382,500 in SGM grant funding
Pleasant Valley Basin | Camarillo Stormwater Diversion to WRP Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | Funded | Received $332,000 in SGM grant funding. No points for funding because the projects is a feasibility study.
| Camarillo Airport Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| Camarillo Desalter Expansion Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| Camarillo Hills Drain Diversion to WRP Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| Camarillo Infiltration Basin Feasibility Study | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 49 | No points for funding because the projects is a feasibility study.
| FCGMA Installation of multi-depth monitoring wells at 3 locations in the Pleasant Valley Basin | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | NA |  | NA |  | NA |  | No | 1 | Funded | Received $1,075,000 in SGM grant funding
| FCGMA Installation of 3 shallow monitoring wells in the Pleasant Valley Basin | <500 AFY | 5 | No Documentation | 5 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Underway and approvals expected <1 year | 4 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | NA |  | NA |  | NA |  | No | 1 | Funded | Received $382,500 in SGM grant funding
Las Posas Valley Basin | VCWWD-1 Moorpark Desalter | <500 AFY | 5 | No Documentation | 5 | Possible by 2040, but uncertain | 5 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 30
| VCWWD-1 Arroyo Las Posas Stormflow Diversion | <500 AFY | 5 | No Documentation | 5 | Possible by 2040, but uncertain | 5 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Low complexity, uses readily available proven technology | 5 | Required, not started and/or potential eminent domain | 1 | Not dependent on other unbuilt projects | 5 | <5 years | 1 | NA |  | NA |  | NA |  | No | 1 | 30

## Project Ranking Criteria
Category | FCGMA Evaluation Criteria Scores
| Water Supply |  |  |  | Timing / Feasibility | [13 empty] | Cost & Funding | [6 empty] | Additional Benefits
| Total Sustainable Yield/ Supplemental Water/ Reduced Demand |  | Sustainable Yield/ Supplemental Water/ Reduced Demand Documentation |  | Project Implementation Timeframe |  | Development Phase |  | Status of Approvals, Permits, and Environmental Review |  | Project Complexity |  | Land Acquisition |  | Dependency on Other Projects |  | Project Lifespan |  | Water Cost |  | Funding Match for Construction |  | O&M Funding |  | DAC Benefits
1 | <500 AFY | 5 | No Documentation | 5 | Post 2040 | 1 | Conceptual - no feasibility or design, project not well defined | 1 | Permit requirements not identified or unknown | 1 | Very complex relies on unproven technology | 1 | Required, not started and/or potential eminent domain | 1 | Project is dependent on other unbuilt and unfunded projects | 1 | <5 years | 1 | >$3000 / AF | 1 | No Match | 1 | No funding identified | 1 | No | 1
2 | 500 to <2500 AFY | 10 | Conceptual Estimate - limited documentation | 10 | Possible by 2040, but uncertain | 5 | FS in progress, project well defined | 2 | Expected to take >5 years | 2 |  | - | Process started but less than 25% complete | 2 |  | - |  | - | $2000 to $3000 / AF | 5 | <10% match | 4 | Up to 25% | 4 | - | -
3 | 2500 to <5000 AFY | 15 | Initial FS supporting estimate | 15 | Operational by 2040 | 10 | Initial Feasibility study completed | 3 | Underway and approvals expected < 3 years | 3 | Moderately Complex | 3 | >25 % < 50% complete | 3 | Project is dependent on funded projects under construction | 3 | 10 Years | 3 | $1000 to $2000 /AF | 10 | 10 to 25% match | 8 | Between 25 and 50% of funding committed | 8 | - | -
4 | 5000 to <7500 AFY | 20 | Prelim Design and / or modeling supporting estimate | 20 | Operational by 2033 | 15 | 30% engineering design | 4 | Underway and approvals expected <1 year | 4 |  | - | >50% complete | 4 |  | - |  | - | $500 to $1000 / AF | 15 | 25 to 50% match | 12 | Between 50 and 75% | 12 | - | -
5 | > 7500 AFY | 25 | Detailed design and / or modeling supporting estimate | 25 | Operational by 2028 | 20 | 60% or greater engineering design | 5 | Permitting and CEQA/ environmental review complete | 5 | Low complexity, uses readily available proven technology | 5 | Not required or all acquisitions an/or easements complete | 5 | Not dependent on other unbuilt projects | 5 | >20 years | 5 | <$500 / AF | 20 | >50% match | 15 | 100% of funding committed | 15 | Yes | 5